## Issues_Updates
Date | Time | Sender | Type | Details
9/15/25 | 9:23 PM | Will | admin, panel, review | Did we ever get access to the admin panel? Dex and I seem to be missing this. Dex will send you a file to review before the meeting, and we can discuss in depth on the call on Wednesday.
9/17/25 | 12:27 AM | Dex | admin, panel | I am still waiting for the admin panel. Alternatively, can we schedule a meeting with the previous developer so Will and I can discuss the web & app with them? 9/17/25, 12:48 AM - Will Dufresne added Sarah Blickenstaff
10/8/25 | 10:06 PM | Carla | admin, login | https://thensnanny.com/login admin@gmail.com Ab2fab2780$
10/17/25 | 5:38 PM | Danny | update | Good morning, just checking in on a status update, how is everything going? Timeline?
11/4/25 | 8:27 PM | Dex | edit | Yes, content for about us <This message was edited>
11/7/25 | 12:06 PM | Dex | change | <Media omitted> 11/12/25, 8:44 AM - ~ Gina Zalesky changed this group's icon 11/12/25, 8:44 AM - ~ Gina Zalesky changed the group name from "Northshore Nanny" to "Syttr"
12/1/25 | 11:23 PM | Dex | api | Just learning about checkr api key
12/2/25 | 1:36 AM | Dex | api | I'm working on its api key
12/15/25 | 8:55 PM | Carla | change | Yes- we have a couple changes we’ll discuss on our meeting Wednesday.
12/15/25 | 9:11 PM | Dex | issue | Please try accessing the application in incognito or private mode. Since the application is designed specifically for mobile use, accessing it via the website may be the reason you are encountering this issue.
12/16/25 | 1:52 AM | Dex | edit, update, updated | Link is Updated <This message was edited>
12/17/25 | 7:46 PM | Carla | login | I was not able to login on as parent. And on nanny side- adding a photo to my account was not working and i could not get past the complete profile page
12/17/25 | 7:47 PM | Dex | edit | carla@gmail.com Test123 use this credentials for nanny d@d.com Test123 Use this for parent <This message was edited>
12/17/25 | 7:55 PM | Dex | fix | Fixing it
12/17/25 | 10:46 PM | Will | change | I will change the meeting to 12/18 noon CST
12/19/25 | 9:52 PM | Carla | edit | Yes for now- i would like to see how it looks all together <This message was edited>
12/21/25 | 4:01 AM | Dex | change, update, updated | I have revised the link. I have not yet made changes to the nanny section, allowing you to compare the previous design with the newly updated version.
12/22/25 | 11:48 PM | Carla | edit, update | Gina sent updates and edits to will- you guys can go through them and get back to me whenever if you have questions. I’m available tomorrow 11-2 if you want to meet to go over anything before the holidays
12/24/25 | 12:48 AM | Dex | update, updated | Link is updated now
12/30/25 | 10:16 PM | Dex | update | Hi @⁨~Danny Z⁩, I'm still waiting for feedback in the current update.
12/30/25 | 10:18 PM | Gina | change | Did will share our notes? It looks like nothing has changed since we sent those over
12/31/25 | 1:02 AM | Dex | update, updated | Updated
1/1/26 | 12:53 AM | Gina | update, updated | Here are the FAQs, lmk when the link is updated!
1/3/26 | 12:39 AM | Gina | change | @⁨Dex⁩ do you think you could send a new link? The old one doesn’t show the changes we made on Wednesday
1/4/26 | 10:31 PM | Dex | update | I have inserted a placeholder on the initial screen regarding the new update. If it is not visible to you, kindly refresh the browser page to ensure you view the most recent update.
1/6/26 | 9:52 PM | Gina | issue | They’re linked to two different accounts is that an issue
1/7/26 | 6:57 AM | Carla | edit | @⁨Dex⁩ can you meet Thursday at 1:30 with Gina and i to go over edits?? And then @⁨Will Dufresne⁩ up to you to have a meeting tomorrow at noon?
1/7/26 | 7:00 AM | Carla | edit, update | If there are any updates on background checks? Or anything you need to discuss- i pretty much just have edits for @⁨Dex⁩
1/8/26 | 5:27 AM | Dex | admin | https://syttradmin.alitacode.com/ email: carla@syttr.com Password: Dex123
2/12/26 | 10:09 PM | Dex | edit, review, update, updated | Hello everyone, Finalizing and reviewing all revisions Will updated it in a while <This message was edited>
2/18/26 | 8:02 PM | Dex | update | I am waiting for feedback over last update
2/18/26 | 8:03 PM | Danny | update | @⁨~Carla Zalesky⁩ @⁨~Gina Zalesky⁩ do you have access to the new update?
2/19/26 | 1:15 AM | Carla | change | Date change And should time/date should mot go away the second i click on one
2/28/26 | 12:00 AM | Gina | fix, fixed | Can you please check every page to make sure the display is right for all phone types? It should automatically adjust to whatever display size the users phone is. Even after you fixed that page, the settings and messages pages are messed up and i didn’t even look at every page.
3/2/26 | 10:05 PM | Carla | update | Will is sending over update at the end of the day
3/3/26 | 6:28 AM | Carla | change | I changed it to a text authentication
3/10/26 | 12:27 AM | Carla | issue, payment | @⁨Dex⁩ 1. Did we not talk about this in our last meeting? Parent books babysitter for time they need- sitter is paid for booking time If the parent needs more time say an hour- they request an hour from the babysitter and the babysitter can then accept or decline offer. Payment should automatically be added and calculated to final amount. 2. If sitter does not arrive at location or cancels within 24 hours punishment goes to rating we talked about in meeting. If parent cancels within 24 hours they get charged 50$. Outside of 24 hours no fee. 3. ⁠please clarify what sos button is. 4. ⁠i think if the nanny has the option to turn on live sharing (location services) i just don’t know if then we run into legal privacy issues
3/10/26 | 12:32 AM | Sarah | payment | 1. We want to confirm the check in process. Current setup is for the parent to complete the job from their end, and the payment automatically sends to the sitter/percentage taken out for you guys. We then confirmed the extend time feature, which will be added. No additional check in/out procedures will be implemented (sitter hitting check in button for job, gps tracking, etc.) correct?
3/10/26 | 1:03 AM | Sarah | ios | Agreed. We will send over a comparison of several babysitting apps, as well as task rabbit, and how they handle these scenarios. To help make a decision
3/12/26 | 6:06 AM | Dex | testflight | @⁨~Carla Zalesky⁩ @⁨~Ryan⁩ @⁨~Gina Zalesky⁩ I have invited you for th latest version of the app please check your email and accept invitation so you can see the app on TestFlight
3/12/26 | 6:06 AM | Dex | payment | For syttrs 1@gmail.com tdexter331@gmail.com For parents 2@gmail.com Password Test1234 Make payment through 0077 card so you can test withdraw as well
3/12/26 | 6:42 AM | Dex | testflight | Step 1: go to the invitation email hit view in testflight Step 2: it will show you the application Step 3: download it If you need my help feel free to cal me
3/13/26 | 9:04 PM | Ryan | Bug | Ya ur card is on there but stilll won’t let me book the job <This message was edited>
3/13/26 | 9:12 PM | Ryan | change | Cool and just need to change all the carla@syttr.com to support@syttr.com throughout the app
3/13/26 | 9:49 PM | Carla | Bug | I can’t logon to admin either
3/13/26 | 10:39 PM | Dex | admin, fix, fixed | Admin fixed @⁨~Carla Zalesky⁩
3/13/26 | 11:46 PM | Carla | edit | I also have some edits to send before the next version so maybe hold off until i send these over
3/14/26 | 1:59 AM | Dex | update | You all might receive an update of the app @⁨~Carla Zalesky⁩ @⁨~Ryan⁩
3/17/26 | 2:14 AM | Dex | review | Hi @⁨~Carla Zalesky⁩ @⁨~Ryan⁩ i would like to take a review on syttr
3/17/26 | 11:49 PM | Sarah | admin, issue, problem, review | Support tickets would be for users to report an issue and get help directly through the app. things like refund requests, billing problems, or job disputes. This helps you review situations and keeps things organized on the admin side
3/18/26 | 10:34 PM | Dex | admin, panel | Im working on connecting your calendar with the admin panel so i believe i put a static time there
3/18/26 | 10:49 PM | Carla | change | Okay for now just keep it open for them to pick whatever time works for them. If i need to change a specific interview I’ll contact them
3/20/26 | 7:26 PM | Dex | admin | Admin-syttr.dexwithteam.com
3/25/26 | 1:13 AM | Dex | change | And on the request that you asked me to change has been done I am uploading it
3/25/26 | 9:21 PM | Sarah | change | Currently the form submissions show up in our CRM. We can change that to also send you an email
3/27/26 | 2:06 AM | Dex | update, updated | Hi @⁨~Carla Zalesky⁩, Could you please provide us the updated credentials for thw aws server?
3/30/26 | 5:51 PM | Carla | issue | Yes- for testing purposes for us. How do we go about this if there are issues though?
4/5/26 | 6:46 AM | Dex | fix, fixed | Uploaded and fixed
4/14/26 | 6:04 PM | Gina | edit | Small thing, when I open the app the first like 1 or 2 seconds there’s a grid which makes the app look like it’s still being edited.
4/14/26 | 6:05 PM | Gina | change, payment | Also, I just paid for and submitted my background check. We need to change the screen after syttrs submit this payment because they might forget if they did the background check and pay for it again
4/14/26 | 6:06 PM | Gina | notification, payment, review | Like after submitting background check and payment it should be a screen saying “your background check is under review, you will receive a notification soon with next steps!”
4/14/26 | 10:46 PM | Gina | admin | Do you have the new admin portal link?
4/15/26 | 1:19 PM | Dex | admin | admin-syttr.zyronexlab.com 4/15/26, 1:19 PM - ~ dwt pinned a message
4/16/26 | 12:42 AM | Gina | admin | After logging into admin the screen went blank and says “Not Found The requested URL was not found on this server.”
4/24/26 | 7:50 PM | Dex | testflight | Its done and uploaded on testflight to test it
4/28/26 | 3:31 AM | Carla | admin | @⁨Dex⁩ my account says verified on admin and not verified on app
5/1/26 | 10:21 PM | Carla | edit, payment | I should be able to add payment from here instead of now going to payment page and adding credit card and redoing all my credentials to hire
5/6/26 | 2:57 AM | Carla | notification | I never got any notifications saying Gina accepted my job offer for today